## Task_Data
Tel Aviv Museum of Art
Task_Name | Duration | Start_Date | Finish_Date | Predecessors
1. Scope Definition | 9 days | February 5, 2018 8:00 AM | February 15, 2018 5:00 PM
1.1 List problems, opportunities, directives and document in project proposal | 9 days | February 5, 2018 8:00 AM | February 15, 2018 5:00 PM | 1SS
1.2 Negotiate scope | 9 days | February 5, 2018 8:00 AM | February 15, 2018 5:00 PM | 1SS
1.3 Plan the project | 9 days | February 5, 2018 8:00 AM | February 15, 2018 5:00 PM | 1SS
1.4 Gather documentation | 9 days | February 5, 2018 8:00 AM | February 15, 2018 5:00 PM | 1SS
2. Problem Analysis | 7 days | February 16, 2018 8:00 AM | February 26, 2018 5:00 PM | 1,2,3,4,5
2.1 Analysis of current example systems | 7 days | February 16, 2018 8:00 AM | February 26, 2018 5:00 PM | 6SS
2.2 Establish key Objectives | 7 days | February 16, 2018 8:00 AM | February 26, 2018 5:00 PM | 6SS
2.3 Update the Project Plan | 7 days | February 16, 2018 8:00 AM | February 26, 2018 5:00 PM | 6SS
2.4 Present the findings in document form | 7 days | February 16, 2018 8:00 AM | February 26, 2018 5:00 PM | 6SS
2.5 Gather documentation | 7 days | February 16, 2018 8:00 AM | February 26, 2018 5:00 PM | 6SS
3. Requirements Analysis | 23 days | February 27, 2018 8:00 AM | March 29, 2018 5:00 PM | 6,7,8,9,10,11
3.1 Identify Business requirements | 23 days | February 27, 2018 8:00 AM | March 29, 2018 5:00 PM | 12SS
3.2 Analyze System's requirements | 23 days | February 27, 2018 8:00 AM | March 29, 2018 5:00 PM | 12SS
3.3 Prioritize business and system requirements | 23 days | February 27, 2018 8:00 AM | March 29, 2018 5:00 PM | 12SS
3.4 Gather documentation and update project plan | 23 days | February 27, 2018 8:00 AM | March 29, 2018 5:00 PM | 12SS
4. Logical Design | 46 days | March 30, 2018 8:00 AM | June 1, 2018 5:00 PM | 12,13,14,15,16
4.1 Logical System Models | 46 days | March 30, 2018 8:00 AM | June 1, 2018 5:00 PM | 17SS
4.2 Specifications of Logical Design | 46 days | March 30, 2018 8:00 AM | June 1, 2018 5:00 PM | 17SS
4.3 Gather documentation and update project plan | 46 days | March 30, 2018 8:00 AM | June 1, 2018 5:00 PM | 17SS
5. Decision Analysis | 31 days | June 4, 2018 8:00 AM | July 15, 2018 5:00 PM | 17,18,19,20
5.1 Identify Candidate solutions | 31 days | June 4, 2018 8:00 AM | July 15, 2018 5:00 PM | 21SS
5.2 Analyze Candidate solutions | 31 days | June 4, 2018 8:00 AM | July 15, 2018 5:00 PM | 21SS
5.3 Recommend a target solution | 31 days | June 4, 2018 8:00 AM | July 15, 2018 5:00 PM | 21SS
5.4 Recommend a project soluion | 31 days | June 4, 2018 8:00 AM | July 15, 2018 5:00 PM | 21SS
6. Physical Design | 13 days | July 16, 2018 8:00 AM | August 1, 2018 5:00 PM | 21,22,23,24,25
6.1 Physical Database design | 13 days | July 16, 2018 8:00 AM | August 1, 2018 5:00 PM | 26SS
6.2 Physical business process and software design | 13 days | July 16, 2018 8:00 AM | August 1, 2018 5:00 PM | 26SS
6.3 Physical user and system interface design | 13 days | July 16, 2018 8:00 AM | August 1, 2018 5:00 PM | 26SS
7. Construction & Testing | 22 days | August 2, 2018 8:00 AM | August 31, 2018 5:00 PM | 26
7.1 Test system to satisfy business requirements | 22 days | August 2, 2018 8:00 AM | August 31, 2018 5:00 PM | 26SS
7.2 Create and revise final documentation | 22 days | August 2, 2018 8:00 AM | August 31, 2018 5:00 PM | 26SS
8. Installation & Delivery | 11 days | September 3, 2018 8:00 AM | September 17, 2018 5:00 PM | 30
8.1 Train system users to use the system | 11 days | September 3, 2018 8:00 AM | September 17, 2018 5:00 PM | 33SS
8.2 Write and implement user manuals | 11 days | September 3, 2018 8:00 AM | September 17, 2018 5:00 PM | 33SS
8.3 Convert existing files to new database | 11 days | September 3, 2018 8:00 AM | September 17, 2018 5:00 PM | 33SS
8.4 Final testing & post-audit review | 11 days | September 3, 2018 8:00 AM | September 17, 2018 5:00 PM | 33SS