## Slide 1: Proposal for the Gallery information system development project
for the Tel Aviv Museum of arts

## Slide 2: Table of content
Definition of scope
  Problem statement
  Constraints
  Scope creep
  Business functions
Goals
Schedule of Project
Budget
Proposed solution
  Business requirements
  Existing problems
  User requirements
  Opportunity to improve
  Risks/ Uncertainties

## Slide 3: 1.DEFINITION OF SCOPE A. PROBLEM STATEMENT
The previous information system does not satisfy the system user requirements anymore; therefore a new improved system needs to be implemented. In order to satisfy the system user’s requirements the newly implemented system needs to facilitate better productivity and improve system performance.
The information system will provide:
A database containing detailed information about the art work.
The database will contain items that are for sale and items that are not for sale.
System will provide an interface that will allow the user to Add, update and delete information.
Program will support the different management functions listed below.

## Slide 4
B. Constraints
Possible constraints for the execution and implementation of a new system. The primary constrain may include need for funds, or colour template used in the graphical user interface. Some other constraints include: Employees’ fear of changing information systems, therefore resisting learning new information system.
C. Scope creep
A general manager and systems analyst will be overseeing the entirety of the system to ensure that the requirements should not overrun the proposed budget.

## Slide 5: D. BUSINESS FUNCTIONS
Commercial manager
A Commercial manager is a manager that is responsible for the selecting and sales of artwork and for the day-to-day activities.
Purchasing management
Purchasing manager is responsible for buying artwork.
Logistics management
Logistics is the management of the movement of goods between point of origin to the point of sale.
Human Resource management
Human Resource management focus on activities concerning the employees.
Financial management
Financial management is concerned with planning and managing the business’s funds in order to achieve the business’s objective.

## Slide 6: 2. Goals
Simplify the user’s tasks.
Provide security, integrity, confidentiality, and privacy.
Improve communication and collaboration.
Improve the processes and processing time.
Provide a friendly and understandable graphical users interface.

## Slide 7: 3. Schedule of Project
Project Steps | Steps Implemented | Proposed date
Scope definition | Scope definition documented in the project proposal. | 25-02-2018
Problem analysis | The project proposal with the existing problems, proposed solutions to the problems, business opportunities, risks, schedule of events and the economic justification. | 25-02-2018
Requirements analysis | Business requirement statements. | 28-03-2018
Logical design | Specifications and the logical design’s system modules | 28-03-2018
Decision analysis | Documentation evaluating each solution in terms of the technical, operational, scheduling, and risk-feasibilities. The best solution will be discussed and chosen. Project will be continued or ended based on decision by all parties. | 28-03-2018
Physical design & integration | Detailed specifications, prototypes, Redesigned business process will be set up. Also, the physical design modules will be executed. | 20-04-2018
Construction & testing | Database construction. Database testing & integration. Custom-built software where purchased software is lacking. User interfaces and test plan executed. | 20-04-2018
Installation | Operation manual set up. Operating system integration, detailed quality review and updated logical system modules constructed. Presentation of the implemented system. | 14-05-2018

## Slide 8: 4. Budget
Internal cost
= 15% of 1 person working 9 hours a day for 6 days a week for 5 months @ R 35/hour
= 15% x (1person x 9 hours x 6days x 4 x 5 x 35)
= R 5 670
Consultant Cost
= 15% of 3 people working 7 hours a day for 5 months @ R113 / hour
= 15% x (3 person’s x 7 hours’ x 6 days a week x 4 x 5 months’ x 113)
= R 42 714
HARDWARE:
Desktop Computer
Dell Inspiron 3668 Desktop computer R7 865
(Mouse and keyboard is included)
Dell S2715H 27” LED Full monitor R4 845
Total Cost
R 5 670 +R 42 714+ R 4 845+ R 7 865
= R 61 094

## Slide 9: 5. Proposed solution
A. BUSINESS REQUIREMENTS
Entities
Process
Add knew artist to the system
Reporting
Sales
Comission
Artwork
Add artwork to the system
Book event for introduction
Selling of artwork
Upkeep of system
Clients
Artist
Events
Inventory
Maintenance of Gallery

## Slide 10: B. EXISTING PROBLEMS
Database
The information system does not provide full information about an art piece e.g. The system only provides the name of the artist and estimated value.
Databases does not support the all the requirements of the system.
Software
The gallery uses outdated software and hardware.
The gallery does not use a uniformed information system ex. The gallery makes use of different application.
Administration of financial activities e.g. The system did not show any commission or statements obtained when selling the art work.
Does not support maintenance of system ex. Cannot update information of the art.
General
Information system does not provide support remote access support.
Not all records have been digitised. Records are currently in the organization’s journals.
The system does not provide a calendar for booking events.
Packaged software is too expensive to use and doesn’t support the gallery’s information system fully.

## Slide 11: C. REQUIREMENTS
Database
A system that provides a full description of the artwork e.g. provide the name of the artist, type of artwork, name of the art piece, collection’s name and price.
Database that supports all the requirements.
Provide a way to add new clients to the organization’s database.
Interface
User interface that is easy to master and is consistent.
Provide a help function for the user.
Use the similar terminology throughout the system.
Caption of the button and menus of the system should be easy to read, understandable and specific.
Number of records the system should be able to hold.
Software
Uniform system.
A system that is easy to integrate with other systems.
Incorporate remote access systems.
Create an electronic calendar for events booking.
The response time should not take too long to process information,
The time a record should be held in the system.
Confidentiality and security e.g. users should provide password and usernames.

## Slide 12: D. Opportunity to improve
Selling of artwork online
With the rise in global art markets eCommerce and eBusiness is necessary to compete with competitors.
Sending notifications for employees
To ensure that all employees are aware of meetings, events and day-to-day activities in terms of the gallery.
Gallery’s hardware may not support the new information system.
System users may not like or understand the output of the new information system.
System users and owners might not be satisfied with the information system.
E. Risk/ uncertainties